## Sheet1
PHYSIOTHERAPY ACTION PLAN
PRC/Hospital __Solferino_________ PERIOD __/__/____ to __/__/____ | [9 empty] | Structure of overall plan | [11 empty] | Reporting timeframes (specific to each ICRC PRP) |  |  | Comments
No. | SMART Objectives | Actions | Resource Needs | Indicators | Time frame | Who | Action completed date | Objective achieved date | Objective discont. date | X = work in progress; C = completed; M = monitor/review; R = report | [11 empty] | M = Monthly; BM = Bimonthly; A = Annual; O = Other
Date started
[10 empty] | J | F | M | A | M | J | J | A | S | O | N | D | Report Name | To whom | Date Completed
1 | By the end of next month all material in the physio department is clean, safe and repaired, otherwise dismissed, to be ready for use. | 1. each Friday afternoon 3-5 pm meeting; 2. dismiss unusable stuff; 3. list what repairs have to be done with which material; 4. two groups parallel: 1 cleans, 2 repairs; then change (acc to skills), 5. ... | 1. cleaning material (10 cleaning cloths, 2 bottles of dish liquid, 1 bottle of detergent, ...); 2. three repair kits and tools; 3. ... | 1. hygiene check acc to checklist: OK; 2. function check of all equipment and devices by PT team: OK; 3. inappropriate, not-to-repair, unused equipment is thrown away | 6 weeks | PT x,y,z: cleaning; PT a,b,c: repair and maintenance; PT v,w: waste removal | 31. of next month | 31. of next month
2 | By the end of this trimester all material and equipment in the physio department is listed in an inventory, which is stored on PC and printed on a sheet attached inside the big physio cupboard | ... | ... | ... | .. | ..
3 | By the end of this trimester a "use of PT equipment" sheet is created to monitor use of equipment and ideas for use ... Based on evidence where possible.